## Sheet1
Review ID | Review Date | Reviewer(s) | Phase | Review Type | Item Reviewed | Linked Task/Item | Summary of Findings | Comments | Status
RVW-001 | 2025-04-06 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SIQ | SIQ_FEAT001_001 | No need for email verification to create an account. | It is not required to send a verification mail to make an account ,just we can check if the account is used before or not | Approved
RVW-002 | 2025-04-06 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SIQ | SIQ_FEAT002_002 | Admin can not delete users | Admin should add menus,add new items , delete items,add and delete offers and promotions, not delete users | Approved
RVW-003 | 2025-04-06 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SIQ | SIQ_FEAT004_001 | Items should be categorized | Items should be categrized | Approved
RVW-004 | 2025-04-06 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SIQ | SIQ_FEAT005_001 | The question is not enough | The question is not clear enough | Approved
RVW-005 | 2025-04-06 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SIQ | SIQ_FEAT001_002 | No Comment | No Comment | Approved
RVW-006 | 2025-04-06 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SIQ | SIQ_FEAT003_002 | No Comment | No Comment | Approved
RVW-007 | 2025-04-06 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SIQ | SIQ_FEAT003_003 | No Comment | No Comment | Approved
RVW-008 | 2025-04-06 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SIQ | SIQ_FEAT006_001 | No Comment | No Comment | Approved
RVW-009 | 2025-04-06 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SIQ | SIQ_FEAT007_001 | No Comment | No Comment | Approved
RVW-010 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT001_001 | this requirement will be detailed in SRS | this requirement will be detailed in SRS to know the criteria of strong password | Rejected
RVW-011 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT002_001 | No Comment | No Comment | Approved
RVW-012 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT002_002 | No Comment | No Comment | Approved
RVW-013 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT002_003 | No Comment | No Comment | Approved
RVW-014 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT003_001 | No Comment | No Comment | Approved
RVW-015 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT003_002 | No Comment | No Comment | Approved
RVW-016 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT003_003 | The requirement description must be clear, concise, and easily understandable to ensure that all stakeholders can interpret it correctly. | requiremt description need to be more clear | Approved
RVW-017 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT004_001 | No Comment | No Comment | Approved
RVW-018 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT005_001 | requirement is not completed | the requirement is pending ,till customer send siq answer | Pending
RVW-019 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT005_002 | No Comment | No Comment | Approved
RVW-020 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT006_001 | No Comment | No Comment | Approved
RVW-021 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT006_002 | No Comment | No Comment | Approved
RVW-022 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT006_003 | No Comment | No Comment | Approved
RVW-023 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT006_004 | the requirement is pending ,till customer send siq answer | the requirement is pending ,till customer send siq answer | Pending
RVW-024 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT007_001 | No Comment | No Comment | Approved
RVW-025 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT007_002 | No Comment | No Comment | Approved
RVW-026 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT007_003 | No Comment | No Comment | Approved
RVW-027 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT008_001 | No Comment | No Comment | Approved
RVW-028 | 18/4/2025 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_001 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-029 | 18/4/2026 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_002 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-030 | 18/4/2027 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_003 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-031 | 18/4/2028 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_004 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-032 | 18/4/2029 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_005 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-033 | 18/4/2030 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_006 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-034 | 18/4/2031 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_007 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-035 | 18/4/2032 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_008 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-036 | 18/4/2033 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_009 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-037 | 18/4/2034 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_010 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-038 | 18/4/2035 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_011 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-039 | 18/4/2036 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_012 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-040 | 18/4/2037 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_013 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-041 | 18/4/2038 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_014 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-042 | 18/4/2039 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_015 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-043 | 18/4/2040 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_016 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-044 | 18/4/2041 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_017 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-045 | 18/4/2042 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_018 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-046 | 18/4/2043 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_019 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-047 | 18/4/2044 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_020 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-048 | 18/4/2045 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_021 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-049 | 18/4/2046 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_022 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-050 | 18/4/2047 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_023 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-051 | 18/4/2048 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_024 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-052 | 18/4/2049 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_025 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-053 | 18/4/2050 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_026 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-054 | 18/4/2051 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_027 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-055 | 18/4/2052 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_028 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-056 | 18/4/2053 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_029 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-057 | 18/4/2054 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_030 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-058 | 18/4/2055 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_031 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-059 | 18/4/2056 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_032 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-060 | 18/4/2057 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_033 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-061 | 18/4/2058 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_034 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-062 | 18/4/2059 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_035 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-063 | 18/4/2060 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_036 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-064 | 18/4/2061 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_037 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-065 | 18/4/2062 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SRS | SRS_001_038 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-066 | 18/4/2062 | Saged Wael | Requirment Gathering | Requirment Gathering | SRS | SRS_002_001 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-067 | 18/4/2063 | Saged Wael | Requirment Gathering | Requirment Gathering | SRS | SRS_002_002 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-068 | 18/4/2064 | Saged Wael | Requirment Gathering | Requirment Gathering | SRS | SRS_002_003 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-069 | 18/4/2065 | Saged Wael | Requirment Gathering | Requirment Gathering | SRS | SRS_002_004 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-070 | 18/4/2066 | Saged Wael | Requirment Gathering | Requirment Gathering | SRS | SRS_002_005 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-071 | 18/4/2067 | Saged Wael | Requirment Gathering | Requirment Gathering | SRS | SRS_002_006 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-072 | 18/4/2068 | Saged Wael | Requirment Gathering | Requirment Gathering | SRS | SRS_002_007 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-073 | 18/4/2069 | Saged Wael | Requirment Gathering | Requirment Gathering | SRS | SRS_002_008 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-074 | 18/4/2070 | Saged Wael | Requirment Gathering | Requirment Gathering | SRS | SRS_002_009 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-075 | 18/4/2071 | Saged Wael | Requirment Gathering | Requirment Gathering | SRS | SRS_002_010 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-076 | 18/4/2072 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_003_001 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-077 | 18/4/2073 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_003_002 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-078 | 18/4/2074 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_003_003 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-079 | 18/4/2075 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_003_004 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-080 | 18/4/2076 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_003_005 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-081 | 18/4/2077 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_003_006 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-082 | 18/4/2078 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_003_007 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-083 | 18/4/2079 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_003_008 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-084 | 18/4/2080 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_005_001 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-085 | 18/4/2081 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_005_002 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-086 | 18/4/2082 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_005_003 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-087 | 18/4/2083 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_005_004 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-088 | 18/4/2084 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_005_005 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-089 | 18/4/2085 | Saged Wael | Requirment Gathering | Requirment Gathering | SRS | SRS_004_001 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-090 | 18/4/2086 | Saged Wael | Requirment Gathering | Requirment Gathering | SRS | SRS_004_002 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-091 | 18/4/2087 | Saged Wael | Requirment Gathering | Requirment Gathering | SRS | SRS_004_003 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-092 | 18/4/2088 | Saged Wael | Requirment Gathering | Requirment Gathering | SRS | SRS_004_004 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-093 | 18/4/2089 | Saged Wael | Requirment Gathering | Requirment Gathering | SRS | SRS_004_005 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-094 | 18/4/2090 | Saged Wael | Requirment Gathering | Requirment Gathering | SRS | SRS_004_006 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-095 | 18/4/2091 | Saged Wael | Requirment Gathering | Requirment Gathering | SRS | SRS_004_007 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-096 | 18/4/2092 | Saged Wael | Requirment Gathering | Requirment Gathering | SRS | SRS_004_008 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-097 | 18/4/2093 | Saged Wael | Requirment Gathering | Requirment Gathering | SRS | SRS_004_009 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-098 | 18/4/2094 | Saged Wael | Requirment Gathering | Requirment Gathering | SRS | SRS_004_010 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-099 | 18/4/2095 | Saged Wael | Requirment Gathering | Requirment Gathering | SRS | SRS_004_011 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-100 | 18/4/2096 | Saged Wael | Requirment Gathering | Requirment Gathering | SRS | SRS_004_012 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-101 | 18/4/2097 | Saged Wael | Requirment Gathering | Requirment Gathering | SRS | SRS_004_013 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-102 | 18/4/2098 | Mariam Moustafa | Requirment Gathering | Requirment Gathering | SRS | SRS_006_001 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-103 | 18/4/2099 | Mariam Moustafa | Requirment Gathering | Requirment Gathering | SRS | SRS_006_002 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-104 | 18/4/2100 | Mariam Moustafa | Requirment Gathering | Requirment Gathering | SRS | SRS_006_003 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-105 | 18/4/2101 | Mariam Moustafa | Requirment Gathering | Requirment Gathering | SRS | SRS_006_004 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-106 | 18/4/2102 | Mariam Moustafa | Requirment Gathering | Requirment Gathering | SRS | SRS_006_005 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-107 | 18/4/2103 | Mariam Moustafa | Requirment Gathering | Requirment Gathering | SRS | SRS_006_006 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-108 | 18/4/2104 | Mariam Moustafa | Requirment Gathering | Requirment Gathering | SRS | SRS_006_007 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-109 | 18/4/2105 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_007_001 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-110 | 18/4/2106 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_007_002 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-111 | 18/4/2107 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_007_003 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-112 | 18/4/2108 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_007_004 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-113 | 18/4/2109 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_007_005 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-114 | 18/4/2110 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_007_006 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-115 | 18/4/2111 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_007_007 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-116 | 18/4/2112 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_007_008 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-117 | 18/4/2113 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_007_009 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-118 | 18/4/2114 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_007_010 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-119 | 18/4/2115 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_007_011 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-120 | 18/4/2116 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_007_012 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-121 | 18/4/2117 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_007_013 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-122 | 18/4/2118 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_007_014 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-123 | 18/4/2119 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_007_015 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-124 | 18/4/2120 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_007_016 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-125 | 18/4/2121 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_007_017 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-126 | 18/4/2122 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_007_018 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-127 | 18/4/2123 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_007_019 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-128 | 18/4/2124 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_007_020 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-129 | 18/4/2125 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_007_021 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-130 | 18/4/2126 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_007_022 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-131 | 18/4/2127 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_007_023 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-132 | 18/4/2128 | youssef Samy | Requirment Gathering | Requirment Gathering | SRS | SRS_007_024 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-133 | 18/4/2129 | Seif | Requirment Gathering | Testcase_writing | Testcase | tc_002_001 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-134 | 18/4/2130 | Seif | Requirment Gathering | Testcase_writing | Testcase | tc_002_002 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-135 | 18/4/2131 | Seif | Requirment Gathering | Testcase_writing | Testcase | tc_002_003 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-136 | 18/4/2132 | Seif | Requirment Gathering | Testcase_writing | Testcase | tc_002_004 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-137 | 18/4/2133 | Seif | Requirment Gathering | Testcase_writing | Testcase | tc_002_005 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-138 | 18/4/2134 | Seif | Requirment Gathering | Testcase_writing | Testcase | tc_002_006 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-139 | 18/4/2135 | Seif | Requirment Gathering | Testcase_writing | Testcase | tc_002_007 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-140 | 18/4/2136 | Seif | Requirment Gathering | Testcase_writing | Testcase | tc_002_008 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-141 | 18/4/2137 | Seif | Requirment Gathering | Testcase_writing | Testcase | tc_002_009 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-142 | 18/4/2138 | Seif | Requirment Gathering | Testcase_writing | Testcase | tc_002_010 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-143 | 18/4/2139 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_001 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-144 | 18/4/2140 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_002 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-145 | 18/4/2141 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_003 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-146 | 18/4/2142 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_004 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-147 | 18/4/2143 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_005 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-148 | 18/4/2144 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_006 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-149 | 18/4/2145 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_007 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-150 | 18/4/2146 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_008 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-151 | 18/4/2147 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_009 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-152 | 18/4/2148 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_010 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-153 | 18/4/2149 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_011 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-154 | 18/4/2150 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_012 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-155 | 18/4/2151 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_013 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-156 | 18/4/2152 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_014 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-157 | 18/4/2153 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_015 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-158 | 18/4/2154 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_016 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-159 | 18/4/2155 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_017 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-160 | 18/4/2156 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_018 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-161 | 18/4/2157 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_019 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-162 | 18/4/2158 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_020 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-163 | 18/4/2159 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_021 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-164 | 18/4/2160 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_022 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-165 | 18/4/2161 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_023 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-166 | 18/4/2162 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_024 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-167 | 18/4/2163 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_025 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-168 | 18/4/2164 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_026 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-169 | 18/4/2165 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_027 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-170 | 18/4/2166 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_028 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-171 | 18/4/2167 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_029 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-172 | 18/4/2168 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_030 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-173 | 18/4/2169 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_031 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-174 | 18/4/2170 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_032 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-175 | 18/4/2171 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_033 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-176 | 18/4/2172 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_034 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-177 | 18/4/2173 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_035 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-178 | 18/4/2174 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_036 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-179 | 18/4/2175 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_037 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-180 | 18/4/2176 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_001_038 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-181 | 18/4/2177 | Mariam Elhussiny | Requirment Gathering | Testcase_writing | Testcase | tc_003_001 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-182 | 18/4/2178 | Mariam Elhussiny | Requirment Gathering | Testcase_writing | Testcase | tc_003_002 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-183 | 18/4/2179 | Mariam Elhussiny | Requirment Gathering | Testcase_writing | Testcase | tc_003_003 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-184 | 18/4/2180 | Mariam Elhussiny | Requirment Gathering | Testcase_writing | Testcase | tc_003_004 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-185 | 18/4/2181 | Mariam Elhussiny | Requirment Gathering | Testcase_writing | Testcase | tc_003_005 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-186 | 18/4/2182 | Mariam Elhussiny | Requirment Gathering | Testcase_writing | Testcase | tc_003_006 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-187 | 18/4/2183 | Mariam Elhussiny | Requirment Gathering | Testcase_writing | Testcase | tc_003_007 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-188 | 18/4/2184 | Mariam Elhussiny | Requirment Gathering | Testcase_writing | Testcase | tc_003_008 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-189 | 18/4/2185 | Mariam Elhussiny | Requirment Gathering | Testcase_writing | Testcase | tc_005_001 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-190 | 18/4/2186 | Mariam Elhussiny | Requirment Gathering | Testcase_writing | Testcase | tc_005_002 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-191 | 18/4/2187 | Mariam Elhussiny | Requirment Gathering | Testcase_writing | Testcase | tc_005_003 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-192 | 18/4/2188 | Mariam Elhussiny | Requirment Gathering | Testcase_writing | Testcase | tc_005_004 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-193 | 18/4/2189 | Mariam Elhussiny | Requirment Gathering | Testcase_writing | Testcase | tc_005_005 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-194 | 18/4/2190 | Asmaa Sayed | Requirment Gathering | Testcase_writing | Testcase | tc_004_001 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-195 | 18/4/2191 | Asmaa Sayed | Requirment Gathering | Testcase_writing | Testcase | tc_004_002 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-196 | 18/4/2192 | Asmaa Sayed | Requirment Gathering | Testcase_writing | Testcase | tc_004_003 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-197 | 18/4/2193 | Asmaa Sayed | Requirment Gathering | Testcase_writing | Testcase | tc_004_004 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-198 | 18/4/2194 | Asmaa Sayed | Requirment Gathering | Testcase_writing | Testcase | tc_004_005 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-199 | 18/4/2195 | Asmaa Sayed | Requirment Gathering | Testcase_writing | Testcase | tc_004_006 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-200 | 18/4/2196 | Asmaa Sayed | Requirment Gathering | Testcase_writing | Testcase | tc_004_007 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-201 | 18/4/2197 | Asmaa Sayed | Requirment Gathering | Testcase_writing | Testcase | tc_004_008 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-202 | 18/4/2198 | Asmaa Sayed | Requirment Gathering | Testcase_writing | Testcase | tc_004_009 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-203 | 18/4/2199 | Asmaa Sayed | Requirment Gathering | Testcase_writing | Testcase | tc_004_010 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-204 | 18/4/2200 | Asmaa Sayed | Requirment Gathering | Testcase_writing | Testcase | tc_004_011 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-205 | 18/4/2201 | Asmaa Sayed | Requirment Gathering | Testcase_writing | Testcase | tc_004_012 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-206 | 18/4/2202 | Asmaa Sayed | Requirment Gathering | Testcase_writing | Testcase | tc_004_013 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-207 | 18/4/2203 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_006_001 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-208 | 18/4/2204 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_006_002 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-209 | 18/4/2205 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_006_003 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-210 | 18/4/2206 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_006_004 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-211 | 18/4/2207 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_006_005 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-212 | 18/4/2208 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_006_006 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-213 | 18/4/2209 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_006_007 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-214 | 18/4/2210 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_007_001 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-215 | 18/4/2211 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_007_002 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-216 | 18/4/2212 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_007_003 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-217 | 18/4/2213 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_007_004 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-218 | 18/4/2214 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_007_005 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-219 | 18/4/2215 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_007_006 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-220 | 18/4/2216 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_007_007 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-221 | 18/4/2217 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_007_008 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-222 | 18/4/2218 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_007_009 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-223 | 18/4/2219 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_007_010 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-224 | 18/4/2220 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_007_011 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-225 | 18/4/2221 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_007_012 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-226 | 18/4/2222 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_007_013 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-227 | 18/4/2223 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_007_014 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-228 | 18/4/2224 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_007_015 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-229 | 18/4/2225 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_007_016 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-230 | 18/4/2226 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_007_017 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-231 | 18/4/2227 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_007_018 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-232 | 18/4/2228 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_007_019 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-233 | 18/4/2229 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_007_020 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-234 | 18/4/2230 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_007_021 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-235 | 18/4/2231 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_007_022 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-236 | 18/4/2232 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_007_023 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-237 | 18/4/2233 | Saged Wael | Requirment Gathering | Testcase_writing | Testcase | tc_007_024 | According to SRS and wireframe No Comment | No Comment | Approved
RVW-238 | 18/4/2234 | Saged Wael | Design | design phase | High ,low,class and ui design | Login Design | According to SRS and wireframe No Comment | No Comment | Approved
RVW-239 | 18/4/2235 | youssef Samy | Design | design phase | High ,low,class and ui design | Registration Design | According to SRS and wireframe No Comment | No Comment | Approved
RVW-240 | 18/4/2236 | Saged Wael | Design | design phase | High ,low,class and ui design | Login Design | According to SRS and wireframe No Comment | No Comment | Approved
RVW-241 | 18/4/2237 | Seif | Design | design phase | High ,low,class and ui design | Home&offers Design | According to SRS and wireframe No Comment | No Comment | Approved
RVW-242 | 18/4/2238 | Atef | Design | design phase | High ,low,class and ui design | Restaurant Design | According to SRS and wireframe No Comment | No Comment | Approved
RVW-243 | 18/4/2239 | Mariam Elhussiny | Design | design phase | High ,low,class and ui design | checkout Design | According to SRS and wireframe No Comment | No Comment | Approved
RVW-244 | 18/4/2240 | Mariam Moustafa | Design | design phase | High ,low,class and ui design | Loyality Points Design | According to SRS and wireframe No Comment | No Comment | Approved