## Sheet1
Work_Package_ID | WORK_Package Name | Task Name | owner | Estimated time | Status
FodiesWebApp_Release003_WPK001 | Front-end | UI-Regestration | Youssef | 1 | Completed
|  | UI-Login+design issues | mariam ahmed | 1 | Completed
|  | UI-HomeScreen+design issues | atef | 1 | Completed
|  | UI-Restaurant Page+design issues | seif | 1 | Completed
|  | UI-Offers+design issues | atef | 1 | Completed
|  | UI-Loyality System | mariam moustafa | 1 | Completed
|  | UI-Checkout+design issues | mariam moustafa | 1 | Completed
FodiesWebApp_Release003_WPK002 | Backend | Regestration_Design | Youssef | 6 | Completed
|  | Login_Design | mariam ahmed | 6 | Completed
|  | HomeScreen_Design | atef | 3 | inprogress
|  | Restaurant Page_Design | seif | 6 | inprogress
|  | Offers_Design | atef | 3 | inprogress
|  | Loyality System_Design | mariam moustafa | 3 | inprogress
|  | Checkout_Design | mariam moustafa | 3 | inprogress
|  | ERD | mariam ahmed | 0
|  | DataBase Creation | saged | 0
FodiesWebApp_Release003_WPK003 | PM TASKS | Plan release | saged | 3 | Completed
|  | PMP_comments&fix(Review) | saged | 3 | INPROGRESS
|  | TRELLO_task creation and assignment | saged | 3 | Completed
FodiesWebApp_Release003_WPK004 | Review | Regestration_DesignReview | saged | 3 | Completed
|  | Login_DesignReview | saged | 3 | Completed
|  | HomeScreen_DesignReview | saged | 3 | pending
|  | Restaurant Page_DesignReview | saged | 3 | pending
|  | Offers_DesignReview | saged | 3 | pending
|  | Loyality System_DesignReview | saged | 3 | pending
|  | DataBase Creation-review | saged | 2 | pending
|  | Checkout_DesignReview | saged | 3 | pending
members | available time | estimated | Estimated_ Buffer | Actual
saged(PM) | 35 | 32 | 3 | 11
atef | 12 | 8 | 4 | 22
mariam mostafa | 12 | 8 | 4 | 15
mariam ahmed | 12 | 7 | 5 | 16
youssef | 12 | 7 | 5 | 16
seif | 13 | 7 | 6 | 13
Total | 96 | 69 | 27 | 93
member | Actual (completed) | Actual(Inprogress) | pending | estimated
saged | 16 | 0 | 17 | 0
youssef | 16 | 0 | 0 | 0
mariam ahmed | 16 | 0 | 0 | 0
mariam moustafa | 2 | 13 | 0 | 1.5
atef | 7 | 15 | 0 | 1
seif | 5 | 8 | 0 | 2
total | 62 | 36 | 17 | 4.5
progress | 79%