## Sheet1
Work_Package_ID | WORK_Package Name | Task Name | owner | time
FodiesWebApp_Release003_WPK001 | Front-end | UI-Regestration | Youssef | 1
|  | UI-Login | mariam ahmed | 1
|  | UI-HomeScreen | atef | 1
|  | UI-Restaurant Page | seif | 1
|  | UI-Offers | atef | 1
|  | UI-Loyality System | mariam moustafa | 1
|  | UI-Checkout | mariam moustafa | 1
FodiesWebApp_Release003_WPK002 | Backend | Regestration_Design | Youssef | 6
|  | Login_Design | mariam ahmed | 6
|  | HomeScreen_Design | atef | 3
|  | Restaurant Page_Design | seif | 6
|  | Offers_Design | atef | 3
|  | Loyality System_Design | mariam moustafa | 3
|  | Checkout_Design | mariam moustafa | 3
|  | ERD | mariam ahmed | 3
|  | DataBase Creation | saged | 10
FodiesWebApp_Release003_WPK003 | PM TASKS | Plan release | saged | 3
|  | PMP_comments&fix | saged | 3
|  | TRELLO_task creation and assignment | saged | 3
FodiesWebApp_Release003_WPK004 | Review | Regestration_DesignReview | mariam ahmed | 3
|  | Login_DesignReview | Youssef | 3
|  | HomeScreen_DesignReview | seif | 3
|  | Restaurant Page_DesignReview | mariam moustafa | 3
|  | Offers_DesignReview | seif | 3
|  | Loyality System_DesignReview | atef | 3
|  | DataBase Creation-review | mariam ahmed | 2
|  | Checkout_DesignReview | atef | 3
members | available time | estimated | Estimated_ Buffer | Actual
saged(PM) | 20 | 19 | 1
atef | 12 | 12 | 0
mariam mostafa | 12 | 11 | 1
mariam ahmed | 12 | 12 | 0
youssef | 12 | 10 | 2
seif | 13 | 13 | 0
Total | 81 | 77 | 4 | 0