## Sheet1
Work_Package_ID | WORK_Package Name | Task Name | owner | Estimated time
FodiesWebApp_Release005_WPK001 | Testcase_Execution+Bugreport | Regestration_testexcution&bugreport | mariam ahmed | 4
|  | Login_testexcution&bugreport | youssef | 4
|  | HomeScreen_testexcution&bugreport | seif | 2
|  | Restaurant Page_testexcution&bugreport | atef | 4
|  | Offers_testexcution&bugreport | seif | 2
|  | Loyality System_testexcution&bugreport | mariam moustafa | 2
|  | Checkout_testexcution&bugreport | mariam moustafa | 2
FodiesWebApp_Release005_WPK002 | Bug_analysis_Analysis | Regestration_Buganalysis | youssef | 0
|  | Login_Buganalysis | Mariam ahmed | 0
|  | HomeScreen_Buganalysis | Atef | 0
|  | Restaurant Page_Buganalysis | Seif | 0
|  | Offers_Buganalysis | Atef | 0
|  | Loyality System_Buganalysis | Mariam Moustafa | 0
|  | Checkout_Buganalysis | Mariam Moustafa | 0
FodiesWebApp_Release005_WPK003 | PM TASKS | Release 5 Plan&followup | saged | 4
|  | PMP_comments&fix(Review) | saged | 6
|  | Test_Strategy | saged | 2
|  | TRELLO_task creation and assignment | saged | 2
FodiesWebApp_Release005_WPK004 | Tracebility Matrix | Regestration_RTM | mariam ahmed | 0.5
|  | Login_RTM | Mariam ahmed | 1
|  | HomeScreen_RTM | Atef | 1
|  | Restaurant Page_RTM | Seif | 1
|  | Offers_RTM | Atef | 1
|  | Loyality System_RTM | youssef | 1
|  | Checkout_RTM | Mariam Moustafa | 1
members | available time | estimated
saged(PM) | 18 | 14
atef | 14 | 6
mariam mostafa | 14 | 5
mariam ahmed | 14 | 5.5
youssef | 14 | 5
seif | 14 | 5
Total | 88 | 40.5
member | Actual (completed) | Actual(Inprogress) | pending | estimated
saged
youssef
mariam ahmed
mariam moustafa
atef
seif
total
progress