## Sheet1
Work_Package_ID | WORK_Package Name | Task Name | owner | time
FodiesWebApp_Release003_WPK001 | UI-Design | UI-Regestration | saged | 1
|  | UI-Login | mariam ahmed | 1.5
|  | UI-HomeScreen | Atef | 1
|  | UI-Restaurant Page | Seif | 2
|  | UI-Offers | atef | 1
|  | UI-Loyality System | Youssef | 1.5
|  | UI-Checkout | Mariam moustafa | 2
FodiesWebApp_Release003_WPK002 | System_Design | Regestration_Design | saged | 6
|  | Login_Design | mariam ahmed | 4
|  | HomeScreen_Design | Atef | 3
|  | Restaurant Page_Design | Seif | 5
|  | Offers_Design | atef | 4
|  | Loyality System_Design | Youssef | 6.5
|  | Checkout_Design | Mariam moustafa | 7
FodiesWebApp_Release003_WPK003 | PM TASKS | RELEASE PLAN | saged | 2
|  | PMP_comments&fix | saged | 2
|  | TRELLO_task creation and assignment | saged | 2
FodiesWebApp_Release003_WPK004 | System_Design Design Review | Regestration_DesignReview | Youssef | 3
|  | Login_DesignReview | saged | 3
|  | HomeScreen_DesignReview | mariam ahmed | 2
|  | Restaurant Page_DesignReview | Mariam moustafa | 3
|  | Offers_DesignReview | mariam ahmed | 2
|  | Loyality System_DesignReview | Seif | 4
|  | Checkout_DesignReview | Atef | 2
members | available time | estimated | Estimated_ Buffer | Actual
saged(PM) | 20 | 16 | 4
atef | 12 | 11 | 1
mariam mostafa | 12 | 12 | 0
mariam ahmed | 12 | 9.5 | 2.5
youssef | 12 | 11 | 1
seif | 12 | 11 | 1
Total | 80 | 70.5 | 9.5 | 0