## Sheet1
Work_Package_ID | WORK_Package Name | Task Name | owner | time
FodiesWebApp_Release003_WPK001 | Front-end | UI-Regestration | Youssef | 1
|  | UI-Login+design issues | mariam ahmed | 1
|  | UI-HomeScreen+design issues | atef | 1
|  | UI-Restaurant Page+design issues | seif | 1
|  | UI-Offers+design issues | atef | 1
|  | UI-Loyality System | mariam moustafa | 1
|  | UI-Checkout+design issues | mariam moustafa | 1
FodiesWebApp_Release003_WPK002 | Backend | Regestration_Design | Youssef | 6
|  | Login_Design | mariam ahmed | 6
|  | HomeScreen_Design | atef | 3
|  | Restaurant Page_Design | seif | 6
|  | Offers_Design | atef | 3
|  | Loyality System_Design | mariam moustafa | 3
|  | Checkout_Design | mariam moustafa | 3
|  | ERD | mariam ahmed | 0
|  | DataBase Creation | saged | 0
FodiesWebApp_Release003_WPK003 | PM TASKS | Plan release | saged | 3
|  | PMP_comments&fix(Review) | saged | 3
|  | TRELLO_task creation and assignment | saged | 3
FodiesWebApp_Release003_WPK004 | Review | Regestration_DesignReview | saged | 3
|  | Login_DesignReview | saged | 3
|  | HomeScreen_DesignReview | saged | 3
|  | Restaurant Page_DesignReview | saged | 3
|  | Offers_DesignReview | saged | 3
|  | Loyality System_DesignReview | saged | 3
|  | DataBase Creation-review | saged | 2
|  | Checkout_DesignReview | saged | 3
members | available time | estimated | Estimated_ Buffer | Actual
saged(PM) | 35 | 32 | 3
atef | 12 | 8 | 4
mariam mostafa | 12 | 8 | 4
mariam ahmed | 12 | 7 | 5
youssef | 12 | 7 | 5
seif | 13 | 7 | 6
Total | 96 | 69 | 27 | 0