## Sheet1
Review ID | Review Date | Reviewer(s) | Phase | Review Type | Item Reviewed | Linked Task/Item | Summary of Findings | Comments | Status
RVW-001 | 2025-04-06 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SIQ | SIQ_FEAT001_001 | No need for email verification to create an account. | It is not required to send a verification mail to make an account ,just we can check if the account is used before or not | Approved
RVW-002 | 2025-04-06 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SIQ | SIQ_FEAT002_002 | Admin can not delete users | Admin should add menus,add new items , delete items,add and delete offers and promotions, not delete users | Approved
RVW-003 | 2025-04-06 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SIQ | SIQ_FEAT004_001 | Items should be categorized | Items should be categrized | Approved
RVW-004 | 2025-04-06 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SIQ | SIQ_FEAT005_001 | The question is not enough | The question is not clear enough | Approved
RVW-005 | 2025-04-06 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SIQ | SIQ_FEAT001_002 | No Comment | No Comment | Approved
RVW-006 | 2025-04-06 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SIQ | SIQ_FEAT003_002 | No Comment | No Comment | Approved
RVW-007 | 2025-04-06 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SIQ | SIQ_FEAT003_003 | No Comment | No Comment | Approved
RVW-008 | 2025-04-06 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SIQ | SIQ_FEAT006_001 | No Comment | No Comment | Approved
RVW-009 | 2025-04-06 | Mariam ELhussiny | Requirment Gathering | Requirment Gathering | SIQ | SIQ_FEAT007_001 | No Comment | No Comment | Approved
RVW-010 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT001_001 | this requirement will be detailed in SRS | this requirement will be detailed in SRS to know the criteria of strong password | Rejected
RVW-011 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT002_001 | No Comment | No Comment | Approved
RVW-012 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT002_002 | No Comment | No Comment | Approved
RVW-013 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT002_003 | No Comment | No Comment | Approved
RVW-014 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT003_001 | No Comment | No Comment | Approved
RVW-015 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT003_002 | No Comment | No Comment | Approved
RVW-016 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT003_003 | The requirement description must be clear, concise, and easily understandable to ensure that all stakeholders can interpret it correctly. | requiremt description need to be more clear | Approved
RVW-017 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT004_001 | No Comment | No Comment | Approved
RVW-018 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT005_001 | requirement is not completed | the requirement is pending ,till customer send siq answer | Pending
RVW-019 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT005_002 | No Comment | No Comment | Approved
RVW-020 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT006_001 | No Comment | No Comment | Approved
RVW-021 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT006_002 | No Comment | No Comment | Approved
RVW-022 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT006_003 | No Comment | No Comment | Approved
RVW-023 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT006_004 | the requirement is pending ,till customer send siq answer | the requirement is pending ,till customer send siq answer | Pending
RVW-024 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT007_001 | No Comment | No Comment | Approved
RVW-025 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT007_002 | No Comment | No Comment | Approved
RVW-026 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT007_003 | No Comment | No Comment | Approved
RVW-027 | 2025-04-11 | Saged Wael | Requirment Gathering | Requirment Gathering | CRS | CRS_FEAT008_001 | No Comment | No Comment | Approved