## Sheet1
Work_Package_ID | WORK_Package Name | Task Name | owner | Estimated time | actual time | Pogress
FodiesWebApp_Release005_WPK001 | Testcase_Execution+Bugreport | Regestration_testexcution&bugreport | mariam ahmed | 4 | 3 | 100%
|  | Login_testexcution&bugreport | youssef | 4 | 6 | 100%
|  | HomeScreen_testexcution&bugreport | seif | 2 | 2 | 100%
|  | Restaurant Page_testexcution&bugreport | atef | 4 | 3 | 100%
|  | Offers_testexcution&bugreport | seif | 2 | 2 | 100%
|  | Loyality System_testexcution&bugreport | mariam moustafa | 2 | 1 | 100%
|  | Checkout_testexcution&bugreport | mariam moustafa | 2 | 1 | 100%
FodiesWebApp_Release005_WPK002 | Bug_analysis_Analysis | Regestration_Buganalysis | youssef | 0 | 0 | 100%
|  | Login_Buganalysis | Mariam ahmed | 0 | 0 | 100%
|  | HomeScreen_Buganalysis | Atef | 2 | 2 | 100%
|  | Restaurant Page_Buganalysis | Seif | 0 | 0 | 100%
|  | Offers_Buganalysis | Atef | 0 | 0 | 100%
|  | Loyality System_Buganalysis | Mariam Moustafa | 0 | 0 | 100%
|  | Checkout_Buganalysis | Mariam Moustafa | 2 | 2 | 100%
FodiesWebApp_Release005_WPK003 | PM TASKS | Release 5 Plan&followup | saged | 4 | 3 | 100%
|  | PMP_comments&fix(Review) | saged | 6 | 4 | 100%
|  | Test_Strategy | saged | 2 | 3 | 100%
|  | TRELLO_task creation and assignment | saged | 2 | 2 | 100%
FodiesWebApp_Release005_WPK004 | Tracebility Matrix | Regestration_RTM | mariam ahmed | 0.5 | 0.5 | 100%
|  | Login_RTM | Mariam ahmed | 1 | 1 | 100%
|  | HomeScreen_RTM | Atef | 1 | 1 | 100%
|  | Restaurant Page_RTM | Seif | 1 | 1 | 100%
|  | Offers_RTM | Atef | 1 | 1 | 100%
|  | Loyality System_RTM | youssef | 1 | 1 | 100%
|  | Checkout_RTM | Mariam Moustafa | 1 | 1 | 100%
members | available time | estimated
saged(PM) | 18 | 14
atef | 14 | 8
mariam mostafa | 14 | 7
mariam ahmed | 14 | 5.5
youssef | 14 | 5
seif | 14 | 5
Total | 88 | 44.5
member | Actual (completed) | Actual(Inprogress) | pending | estimated
saged | 12 | 0 | 0 | 0
youssef | 7 | 0 | 0 | 0
mariam ahmed | 4.5 | 0 | 0 | 0
mariam moustafa | 5 | 0 | 0 | 0
atef | 7 | 0 | 0 | 0
seif | 5 | 0 | 0 | 0
total | 40.5 | 0 | 0 | 0
progress | 100%